## Repo
Pro-Inspector Source Repository
URL | https://graveekumar@bitbucket.org/pro-inspector/backoffice.git
Username | graveekumar
Git-Token | ATBBmYL5YCW6cQVEEuv66jffLEER721280FA
Branch | Master & Development

## GAS Tracker
SNo | Environment | Test/Modules | Status | Assigned | Effort
SPRINT I |  |  | Completed |  | 128
1 | Mobile | APK Configuration & Setup | Completed | Team | 2
2 | Web | Login | Completed | Yogesh | 1
3 | Web | Inspection Listing | Completed | Yogesh | 5
4 | Web | Create Inspection | Completed | Yogesh | 8
5 | API | Create API Web Service | Completed | Yogesh | 2
5 | Mobile | Login | Completed | Nithish | 1
9 | Mobile | Inspection Listing | Completed | Nithish | 2
10 | Mobile | Edit Inspection | Completed | Nithish | 3
11 | Mobile | Execute Inspection (Checklists) By Search | Completed | Nithish | 35
12 | Mobile | Execute Inspection (Checklists) By Scroll | OnHold | Nithish
13 | Web | Execute Inspection (Checklists) | In-Progress | Yogesh | 11
14 | Mobile | Add Observation(s) | OnHold | Nithish
15 | Mobile | Complete Inspection | Completed | Yogesh | 4
16 | Mobile | Signature validation | Completed | Yogesh | 4
17 | Mobile | Invoice Generation | Completed | Yogesh | 4
18 | Mobile | View & Share Report | OnHold | Nithish
19 | Web | Certificate Generation | Completed | Yogesh | 4
20 | Integration | TestOps Integration Testing | Completed | Nithish | 12
21 | Integration | TestOps Integration Testing | Completed | Yogesh | 18
22 | Integration | Phase I Review | Completed | Ravi | 9
23 | Pipeline | Azure DevOps Pipeline Configuration | Completed | Team | 3
SPRINT II |  |  | In-Progress |  | 10
1 | Mobile | Create Inspection | OnHold | Nithish | 3
2 | Mobile | Create Entity | OnHold | Nithish | 2
3 | Mobile | Create Object | OnHold | Nithish | 2
4 | Web | Create Entity | In-Progress | Yogesh | 3
5 | Web | Create Object | Yet To Start | Nithish
6 | Web | Schedule Inspection with new entity and object | Yet To Start | Nithish
7 | Web | Schedule inspection with new NIF | Yet To Start | Nithish
8 | Web | Schedule inspection with existing NIF | Yet To Start | Nithish
9 | Web | Schedule inspection with existing NIF entiny and new object (NIF) | Yet To Start | Nithish
10 | Web | Schedule inspection with default NIF | Yet To Start | Nithish
11 | Web | Schedule inspection with invoice address enabled | Yet To Start | Nithish
12 | Integration | TestOps Integration Testing | Yet To Start | Nithish
13 | Integration | Phase II Review | Yet To Start | Ravi

## Reliance Tracker
| SNo | Environment | Test/Modules | Status | Assigned | Date | Planned | Actual | Comments/Remarks
| SPRINT I |  |  | Partially Completed |  |  | 77 | 61
| 1 | BO | Login | Completed | Nithish | 2024-11-27 | 1 | 2
| 2 | BO | Menu & Product Listing | Completed | Nithish | 2024-11-27 | 2 | 2
| 3 | BO | Schedule Audit | Completed | Nithish | 2024-11-27 | 4 | 4
| 4 | BO | Assign Input & Output Activity | Completed | Nithish | 2024-11-27 | 1 | 2
| 5 | BO | Integration Web Test & Review & Enhancement | In-Progress | Nithish | 2024-11-28 | 8 | 5
| 6 | API | Create API Web Service & Validate testAPI | Completed | Yogesh | 2024-11-29 | 1 | 3 | Upgraded the API Change to support multiple endpoint based on client (e.g., Gas, Reliance, etc.). Developed APIs for Reliance.
| 7 | FO | Login | Completed | Nithish | 2024-11-28 | 1 | 1
| 8 | FO | Product & Listing Audits/Inspections by search | Completed | Yogesh | 2024-11-29 | 2 | 2
| 9 | FO | Search & Edit audit details | OnHold |  |  | 2
| 10 | FO | Execute Audit Input & Output Activity | Completed | Yogesh | 2024-11-29 | 1 | 1
| 11 | FO | Execute Inspection/Audit (Checklists) | Completed | Nithish | 2024-12-03 | 8 | 9
| 12 | FO | Create Tasks (NC & Observation) | Completed | Yogesh | 2024-12-03 | 4 | 4 | Unable to open a test Device(Emulator) & Cloud Device for a while
| 13 | FO | Complete Inspection/Audit | Completed | Yogesh | 2024-11-29 | 1 | 1
| 14 | FO | Approve Inspection (Checklists) | Completed | Yogesh | 2024-12-02 | 2 | 2 | UAT Server not avaliable for 1hr
| 15 | FO | Logout & Login with another user(Auditor) | Completed | Yogesh | 2024-12-02 | 1 | 1
| 16 | FO | Edit User Details If | OnHold |  |  | 1
| 17 | FO | Reject Audits - Agree/Disagree Response | Completed | Yogesh | 2024-12-03 | 1 | 1
| 18 | FO | Re-execute & Re-approve | In-Progress | Yogesh | 2024-12-03 | 2 | 1
| 19 | FO | Verify & Confirm Tasks (NC & Observations) by Auditee | Completed | Nithish | 2024-12-04 | 2 | 4 | Delayed by app crashing issue on emulator (Cloud device not avail)
| 20 | FO | Complete Inspection/Audit By admin | Completed | Yogesh | 2024-12-03 | 1 | 1
| 21 | FO | Signature validation | Completed | Yogesh | 2024-12-03 | 1 | 1
| 22 | FO | View & Share Report | Completed | Yogesh | 2024-11-29 | 3 | 1
| 23 | FO | Intagration Mobile Test & Review & Enhancement | In-Progress | Team | 2024-12-03 | 8 | 9 | Unable to open a test Device(Emulator) for a while
| 24 | Integration | Data-Driven Test Suite Configuration | In-Progress | Nithish | 2024-12-03 | 6 | 4
| 25 | Integration | TestOps Integration Testing | Yet To Start | Nithish |  | 10
| 26 | Integration | Phase I Review | Yet To Start | Team |  | 2
| 27 | Pipeline | Azure DevOps Pipeline Configuration | Yet To Start | Nithish |  | 1
| SPRINT II |  |  | In-Progress |  |  | 37 | 17
| 1 | BO | Execute Inspection (Checklists) | Completed | Yogesh | 2024-12-04 | 4 | 5
| 2 | BO | Execute Audit Input & Output Activity | Completed | Yogesh | 2024-12-05 | 2 | 2
| 3 | BO | View & Share Report | Completed | Yogesh | 2024-12-05 | 1 | 1
| 4 | BO | Create Tasks (NC & Observation) | Completed | Yogesh | 2024-12-06 | 3 | 3
| 5 | BO | Complete Inspection/Audit | Completed | Yogesh | 2024-12-06 | 1 | 1
| 6 | BO | Verify & Confirm Tasks (NC & Observations) by Auditee | Completed | Yogesh | 2024-12-06 | 2 | 2
| 7 | BO | Reject Audits - Agree/Disagree Response | Completed | Yogesh | 2024-12-06 | 1 | 1
🟢 | 8 | BO | Re-execute & Re-approve | In-Progress | Yogesh | 2024-12-09 | 2
| 9 | BO | Intagration Web flow 2 Test | Yet To Start | Team |  | 8 | 2
|  | Integration | Phase II Review | Yet To Start | Team |  | 2
|  | Integration | TestOps Integration Testing | Yet To Start | Nithish |  | 10
|  | Pipeline | Azure DevOps Pipeline Configuration | Yet To Start | Nithish |  | 1

## EffortPlan(PI)
As of 22-Novemnber-2024 | Week | Project Hours |  | Nithish | Yogesh | Ravikumar
|  | Planned Hours | Actual Hours
| Week 1 | 80 | 64 | 28 | 32 | 4
| Week 2 | 80 | 60 | 35 | 21 | 4
| Week 3 | 40 | 4 | 3 | 1 | 1
| Total | 200 | 128 | 66 | 54 | 9